Global Mechanism Interim Working Group Conference Call, October 3rd – 10 AM

Meeting notes

Expected outcomes

- Recommendations for streamlining/fine-tuning of implementation plan

- Prioritize key action points/potential quick wins for first six months

- Recommendations/agreement for management structure/resourcing

- Welcome and Review of Agenda

Organizers:

Warren Feek (Communication Initiative) and Rafael Obregon (Unicef)

Participants present:

  - James Deane (BBC Media Action)

  - Sue Goldstein (Soul City)

  - Susan Krenn (JHU)

  - Zehui Dai (ICA, on behalf of Radhika Gajjala)

  - Hope Hempstone (USAID)

  - Antje Becker (Save the Children)

  - Lisa Hilmi (CORE Group)

  - Patrick Cook (International Social Marketing Association)

Note: Everyone should have these three core documents: 1) agenda for today’s call, 2) implementation plan, and 3) a brief TOR. Please follow-up with Warren/Rafael if anyone doesn’t have one of these.

- Overview of Draft Implementation Plan

- Rafael opened with a brief recap of the draft implementation plan report that was circulated (and about the approach that was used to draft the plan):

- The report captures some of the key issues that were raised during the mechanism meeting, consultation process and in the consultation report to guide what we should be doing over the next 12 months, and then less detail for the second year operation of the mechanism.

  - It should provide some background on the key aspects that are critical to how the groups feels we can best move forward, including: operation principles (i.e. what should be the guiding principles and considerations?) and then moving to the implementation plan (ie. i.e. discussing/resolving issues related to the name and broader positioning of the mechanism), mission of the mechanism, and then an elaboration on the 4 priorities that were part of the consultations around the mechanism (i.e. regarding funding, etc.).

- We should be now moving toward agreeing upon the key organizations and partners for this mechanism. Primary recommendation in consultation was that it should be a convening force of many organizations that represent large networks. And this relates to the importance of having representative membership in the mechanism (that everyone has a space and voice in it).

- We realize that some of the key tasks/priorities highlighted in the report might be too ambitious or that there may be too many. But we hope that these can serve as guides to help us determine “quick wins” and “short term actions points” that are achievable for us over the next few months, and to help us facilitate what might be the set-up of certain working groups or subgroups to focus on each of these areas.

- We are very open to your feedback and comments and certainly to hearing about needed adjustments and changes that can be made to ensure we have collective ownership of this plan.

- Round robin of everyone’s top 2 or 3 observations of the plan

  - Patrick Cook (International Social Marketing Association)

This is an amazing amount of work so thank you for pulling this together. A few things jump out to me. In the development of implementation plan we already seem to have some progress of what we want the mechanism to be and I think inadvertently the name has been developed as the Global Alliance with something after that – this works well for us in social marketing community. We think it’s important to start advocating on part of people doing comm for social good, and so we are hoping the advocacy role is a more explicit part of what we want to accomplish.

  - Lisa Hilmi (CORE Group)

Echo the thanks for the work. It’s important for me that the mission, names and priorities should be the top goals to align us and the working groups. I think the name… Communication Alliance may sound too much like Comm Initiative or other related names, so we should probably be thoughtful about how we position the name and ensure we have “global” in there so we are representative of societies and global networks. And we should be a little more detailed about what our priorities are -- and see if they align, for instance, with other development goals or the SDGs, etc so we can be clear what the mission is for this group. I think it’s a clear outline of the priorities and how they can be delineated into working groups.

  - Antje Becker (Save the Children)

I think both documents show a lot of great thinking so I echo the thanks of everyone else. My key thoughts are… you have put forward the need to have communication in the name and that puts me in the minority, because we (Save the Children) are pushing for behavior change – interested in more than communication and this would better reflect the work of Save the Children constituents at the community level. Grappling with that. Also with alliance building and member: do we have criteria on how the members were determined/added in? how were they selected?

We should also be adding key responsibilities of groups that are implementing to make them more actionable.

  - Hope Hempstone (USAID)

I wanted to echo everyone’s thanks. We were impressed with all the thinking and hard work that went into this and the coherent voice captured what was discussed really well. Our primary concern is similar to Antje’s, in reading the implementation plan it seems strongly focused on media and comm approaches to behavior change, and if that is what that is then maybe we should more strongly acknowledge that focus. But if there is a choice to focus on the full breadth of disciplines that were discussed in consultation then we should be more inclusive of those groups coming from non-communication based fields.

We also wondered if it could be hard to gain traction in this effort if we are trying to be all things to all orgs in all regions…so maybe in the short term our primary focus should be on some subset (i.e. communication approaches to MNCH), and then expand into a broader space.

The only other broad based point of feedback is that we thought what was projected for the first year might be too ambitious, and it might be worth pausing to see if this is really doable in the first year. Suggests that having more time to tackle a couple specific priorities could be useful.

  - Zehui Dai (ICA, on behalf of Radhika)

ICA will be having a conference next year around May in Europe. We could have a round table discussion that ties into this project and so we can begin the conceptualization of this meeting as a contribution.

  - Susan Krenn (JHU)

Echo the thanks. Shared many of the observation made about the name. Suggests it also might be important to understand the criteria for who is at the table for this. Also points out that this could be a very heavy lift-off, and that talking to Hope’s point the idea of really finding a quick fast win is important. Perhaps the advocacy agenda?

  - Sue Goldstein (Soul City)

Agrees that it’s a heavy agenda. There are opportunities to meet face to face through other platforms, discussed benefit of an official launch – and to have at least one thing/contribution ready in time for the launch (i.e. related to WHO standards perhaps?). Regarding the name: would like something that’s clear and that everyone understands.

  - James Deane (BBC Media Action)

Personally is an advocate for the terminology of having “Global Alliance” and “society” in the name. Wants to think about what the focus should be – if it cuts across the development agenda then it should have “society” as part of it. Agrees with Sue about having a launch, opportunity to articulate what this means, and suggests thinking more about linking to a high level political forum and to align activities around some of the specific Sustainable Development Goals.

Think about how we could make some quick wins in the development agenda that not everyone else is talking about.

- Rafael provided some summarizing thoughts on the feedback:

- Seems to me that overall we seem to agree on some key issues. I think we need to streamline the set of activities (which I agree are probably too many and too ambitious) as a menu to choose from. I think we also need to come around the issue of the name – in terms of what would be a name that captures and communicates very clearly what this mechanism is about. The more fundamental question I think is what’s been raised in terms of whether this should be either communication focused or should accommodate the broader range of social and behavior change approaches in the field, and I think we should resolve that as it influences what networks are invited, and who sees themselves as part of it, etc. I don’t have an answer at the moment (though he suggests that it would be nice to have both elements reflected) but I think we can have a more dedicated discussion on this and figure out how to frame it, but I also don’t think that should prevent us from moving ahead on the critical issues and action points that I think we all agree on – in order to have a shared agenda. Then, in parallel, we can think about how we can frame the mechanism in a way that addresses the name concerns.

- Likes the suggestion that the Summit could be a great space for a launch.

- Also agrees about the need for quick wins and short-term outputs. Discussed having a quick inventory of initiatives that we can bring into this mechanism (i.e. WHO standards mentioned by Sue, some of the policy briefs that BBC Media Action produces, some ideas around work we are doing with Gates regarding stock-take around key issues in the field, etc.).

- Issues that require clarification / Top priorities for the first 12 months

- Discussion opened-up for additional questions/open forum:

Some points/thoughts raised included:

  - Antje Becker (Save the Children)

Discussion of the term “information engagement”… and whether the notion of “information” is too reductive/narrow term which inadvertently leads us away from behavior change and recent work in the behavioral sciences. 
(Hope agreed with the points raised by Antje)

  - James Deane (BBC Media Action)

Putting people at the heart of this is what’s important. Concerned the name “Comm for Development” isn’t the right wording to sufficiently break into development agenda and is having the side-effect of partitioning the field off as a communication-centered field.

  - Sue Goldstein (Soul City)

I’m thinking maybe we should be thinking about something completely different. Like the “Alliance for People at the Center” or something that gets us outside of the jargon. At the moment we have a name that no one understands, so it has to be something that everyone can relate to. I think the point is to try to not have some really long title that has to be explained in 3 pages, and I think it’s impt that it’s immediately apparent what this group is.

  - Patrick Cook (Social Marketing & Communication)

I agree that I think a name with some resonance now would be helpful as a way to help us have the discussion we want to have with the right people. And I think we want to keep the focus on social and behavior change, and communication is the common thread and so I’d like to see those together. Values Hope and Antje’s concern, thinks we are all here because we at least all share communication in common as being one way to move the development agenda forward.

  - Warren Feek (Communication Initiative)

Thinks the name issue is fundamentally about identity. Wanted it to be something that did not replace or compete with existing networks (eg. Communication Initiative, C4D Network, etc..), but rather a way to show the weight of all these networks by bringing them together.

Thinks we need something that doesn’t immediately cut out key parts of development process (i.e. the democracy and governance arena), but asks what would be 2 or 3 core elements that everyone can identify with?

Whether it’s social change and dialogue at one end and social marketing at the other…we all want people informed and engaged.

Suggests opening-up an online dialogue on this identity/name issue.

- How do we envision working together for the next six to twelve months?

- A couple points raised:

  - Rafael Obregon (in response to a question from James Deane)

Unicef is interested in supporting this for the next 6 months and to see this process going, and so we have some resources to take this work forward, but we would like to discuss with the group how this can be properly resourced over the long-term.

We hope that each of you can make some contributions along the way in terms of some of these immediate outputs, but I think a big question will be about how we can resource this in the long-term once we have come to an agreement and resolve some of the key issues.

  - Lisa Hilmi (CORE Group)

Is there any private sector besides social marketing side that might add some value to this group? And to make sure we are geographically dispersed?

- Next Steps/Closing/Consensus-Building:

Rafael Obregon (Unicef)

- Discusses next steps for moving forward.

- Asks: do we try to address some of these key issues via email in the next few days? Or do we (via email) try to convene smaller groups to look at specific areas or aspects of the implementation plan (i.e. how to streamline specific points, discuss the name and framing of the group, etc.)?

Next Step and Group Consensus:

- Warren to consolidate/share comments provided by each member with the wider group.

- Group agreed that Rafael and Warren will discuss and convene some of these smaller groups, particularly one focused on the name/vision of the alliance, and another one on the priority action points.

- Group agreed that 10AM EST is a good time for everyone to have these meetings/calls.